## Slide 1
Licia Florio
AARC Kick-off, Amsterdam
Authentication and Authorisation for Research and Collaboration
What you need to know about AARC
3-4, June 2015
Project Coordinator, AARC
PDO, GÉANT

## Slide 2: Agenda
AARC Goals
AARC Structure
AARC and T&I ecosystem
Administrative aspects:
  Web space and lists
  Management tools
  Manpower summary
  KPIs
  Procedures and Tools

## Slide 3: AARC Goals
Build on federated access, improve its up-take and address current challenges
Harmonise policies among e-Infrastructures to ease service delivery
  Avoid the creation of project-specific AAIs by enabling researchers to use their existing credentials to access different resources
Define a training package for institutions and services to support federated access
Enable existing AAIs to consume existing user’s credentials

## Slide 4: AARC Structure
JRA1
(GRNET)
To research on technologies to deliver the design of the integrated AAI
NA3
(NIKEF)
To define scalable policies and operational models for the integrated AAI
SA1 (SURFnet)
To pilot key components of the integrated AAI
NA2
(GÉANT)
To train, disseminate and reach out
NA1
(GÉANT)
Overall Management
Liaison with other relevant user communities, e-Infrastructures and international relevant AAI activities

## Slide 5: AARC and T&I ecosystem
AARC
REFEDS/FIM4R
e-Infrastructures i.e. GEANT
eduGAIN
REFEDS:
Pilot the deployments
Incorporate
Develop business case
Costing
Supply chain
Feedback and validation from Fed Operators on best practices
Training
AARC technical and policy findings
Pilots
Anchored in real use cases
Requirements
Feedback on pilots from AAI user communities
FIM4R:
Requirements/feedback for training and architecture
GN4 project, REFEDS, FIM4R, RDA, and various AAI work within other projects
Liaisons with other projects, i.e. CILogon

## Slide 6: AARC Delivery Process
User Requirements
SA1 Pilots
JRA1, NA3 Research and position solutions
NA2 Training

## Slide 7: Where AARC sits
AARC-: 5,5-7,5

## Slide 8: Critical Paths
Training package
Incident response framework and Assurance
  Joint effort AARC, REFEDS, research community and eduGAIN
Dependencies between pilots, the architecture and best practices work
  We need to have a base for SA1 to work on
We need to prepare for the next call – deadline April 2016
  Plan available in Sept

## Slide 9: Procedures, procedures

## Slide 10: Web spaces and mailing lists
Website
  https://aarc-project.eu
  Blog
  NA1 to manage that, WP leaders to manage their space
Wikis
  Private space – to manage the project:
    https://wiki.geant.org/display/AARC/AARC+Private+Space
  Public wiki: for all WPs and tasks to share information
    https://wiki.geant.org/display/AARC/AARC+Home
Mailing lists
  To be migrated to geant.org soon
EventR – to organise meetings
  Federated access, available to everybody who needs it
  But you can use other tools

## Slide 11: Management tools
Smartsheet
  Used by NA1
  You will receive a notification when you are expected to deliver something
Quarterly reports – internal documents
  Not required by the EC but as internal management tool
  See template at: https://wiki.geant.org/display/AARC/NA1+-+Quarterly+Reports
  Feedback is welcome
Time reports
Milestones and Deliverables
  Monitored on the wiki

## Slide 12: KPIs as in the Technical Annex
Impacts | KPIs
Facilitate sharing of research results across disciplines | A research service is available across three disciplinary communities.
Harmonise procedures and policies to ease cross-discipline collaboration | Pilot incident response procedures in 5 IdPs.
Facilitate integration of (commercial) resources | 3 new SPs selected by the community available in eduGAIN,.
Improve inter-operability of e-Infrastructures | At least one generic attribute provider pilot; Adoption of the incident response procedure at 5 IdPs.
Reduced duplication of efforts for developing services common to various e-Infrastructures | 2 cross-infrastructure use cases delivered.
Expand the coverage of federated access | At least 3 new IdPs in the targeted user communities and 3 new SPs
Contribution to the wide SSO for R&E | Enable federated access in at least each community represented in the project and add 2 new services to eduGAIN

## Slide 13: Considerations on the KPIs
We need them to measure our work
Some KPIs impact eduGAIN
  I.e. adding new services to eduGAIN
  Need to work closely with the eduGAIN team
We need to review them and apply them to the WPs
  Particularly the pilots
  And training and outreach

## Slide 14: To Do List
Nominations for the Project Board – rather urgent
WPs detailed plans
Review KPIs

## Slide 15
karl.meyer@geant.org