## Slide 1
NA2 meeting in Brussels, October 26
Authentication and Authorisation for Research and Collaboration
Status and planning ahead
Training module for SPs and resource providers
Outreach and training, AARC
Development manager
Manne Miettinen, CSC

## Slide 2: People working for NA2 T3 at CSC
Ari-Matti Sarén
  Specialised in organising and carrying out trainings for Biomed customers
Mikael Lindén
  Specialist in AAI and the architect of ELIXIR AAI
Tommi Nyrönen
  Biomed services visionnaire
Manne Miettinen
  Coordinator

## Slide 3: What we have done so far
Tried to figure out how to carry out the task
  What are the target organizations like?
  What is the target audience like?
  The training concept
Contacted an Elixir service provider called TeSS (Manchester University)
  A portal of training material for the Elixir community
  Agreed to carry out a training in March 2016
Created the first draft of the SP training module slides
  …by copying SWITCH slides
Contacted possible trainers for the March training
  Lukas Hämmerle and Michal Prochazka in addition to CSC

## Slide 4: The training concept
The target audience
  The ICT people who are going to do the installation
  The benefits of AAI are irrelevant for this audience
  They are few, 1–2 / organization, may need outside help too
A two day event
  Open for all prospective AARC SPs and resource providers (not only TeSS or Elixir)
  Day 1 Hands-on, Installation and configuration of Shibboleth SP in a virtual machine
  Day 2 Hands-on, Research community specific services (ELIXIR, DARIAH/DAASI/CLARIN, EGI, CERN,…)

## Slide 5: The training material
A quick look at the slides

## Slide 6: The interactive part
Is the 2-day concept viable?
What is missing from the training material slides before publishing?
Are you interested in cooperating with the March training event?
Next steps (time table and responsabilities)
  Publishing the training module
  Manchester event
  The next event(s)

## Slide 7
manne.miettinen@csc.fi